## Activities
CTE – Linked Learning · Activities
Edit this tab to update the Gantt automatically. Fill in Start/End for continuous activities, OR Custom months (e.g. "8,10,1,3") for irregular ones.
Workstream | Activity | Start month | End month | Custom months | Effort (1–4) | Milestone? | Who | Notes | Link
CTE Pathway, Scheduling & Funding | CTE master scheduling, pathway completion & Elevate error review |  |  | 1,2,3,4,5,6,7,9,12 | 1 | No | Coaches | Consolidates recurring master-schedule planning, concentrator/capstone checks, and administrator/counselor follow-up.
CTE Pathway, Scheduling & Funding | Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support |  |  | 2,3,4,7,8,9,12 | 2 | No | Coaches | Combines application-window support, deadline follow-up, budget alignment, and award purchasing support.
CTE Pathway, Scheduling & Funding | GSPP planning, implementation & spending support |  |  | 3,5,6,7,8,9,11,12 | 2 | No | Coaches | Includes PD, implementation coaching, goal progress, and spending support.
CTE Pathway, Scheduling & Funding | Course equivalencies development | 2 | 5 |  | 2 | No | Coaches | Equitably assigned course-equivalency work.
Instructional Design, PBL & Defenses | PBL/HQIM annual planning, pilot reflection & improvement design |  |  | 11,12 | 1 | No | Coaches | Consolidates pilot reflection, theory of action, and annual instructional planning.
Instructional Design, PBL & Defenses | PBL/HQIM school-site coaching and professional learning | 3 | 9 |  | 3 | No | Coaches | Core instructional coaching and PD at school sites.
Instructional Design, PBL & Defenses | Linked Learning onboarding / August PBL professional learning | 2 | 2 |  | 2 | Yes | Coaches | Major August onboarding/PBL event; shown on Gantt but excluded from capacity totals as a milestone.
Instructional Design, PBL & Defenses | PBL 101 / fall instructional training | 4 | 4 |  | 3 | No | Coaches | October PBL 101 and related fall instructional training.
Instructional Design, PBL & Defenses | Defense calibration, support, feedback & reflection |  |  | 7,8,9,11 | 2 | No | Coaches | Combines calibration, school support, feedback, and review of defense quality/data.
Pathway Strategy, Data & Certification | Administrator goal-setting, priorities & annual data review |  |  | 1,2,12 | 2 | No | Both | Annual planning and data review with administrators; includes follow-up review of school goals.
Pathway Strategy, Data & Certification | School goal progress checks and targeted support planning |  |  | 4,5,11 | 2 | No | Both | Team reviews progress, identifies patterns, and plans differentiated support.
Pathway Strategy, Data & Certification | Linked Learning certification planning & school support | 2 | 10 |  | 2 | No | Both | Support for schools pursuing Silver, Gold, or other Linked Learning certification milestones.
Pathway Strategy, Data & Certification | Team data checks, accomplishments review & next-year goal setting |  |  | 3,7,11,12 | 1 | No | Both | Includes CTE completion, WBL, MiSiS tagging, CCR/dashboard outcomes, and year-end reflection.
Pathway Strategy, Data & Certification | Cross-team funding review & GSPP 3-year planning |  |  | 9,12 | 1 | No | Both | Funding application scoring and cross-team GSPP planning.
Professional Learning & Leadership | Linked Learning Team retreat | 1 | 1 |  | 1 | Yes | Both | Team retreat / annual launch; milestone excluded from load totals.
Professional Learning & Leadership | Linked Learning Leaders professional learning series |  |  | 3,4,7,8,10 | 2 | No | Coaches | Planning and facilitation of Leaders PD/workshops across the year.
Professional Learning & Leadership | Linked Learning microcredential program | 1 | 11 |  | 1 | No | Coaches | Promotion, facilitation, support-provider coordination, and participant support across the annual cycle.
Professional Learning & Leadership | Administrator Linked Learning information sessions | 1 | 3 |  | 2 | No | Coaches | July–September information sessions for school administrators.
Professional Learning & Leadership | LL Conference, Showcase & recognition activities |  |  | 4,9,10 | 2 | No | Both | Includes conference, CTE-Linked Learning Showcase, and leader/student recognition work.
Professional Learning & Leadership | Department planning, team committees & cross-functional coordination | 2 | 9 |  | 1 | No | Both | Recurring department planning and internal committee work.
Professional Learning & Leadership | School Redesign Grant demonstration site visits |  |  | 3,5,9 | 2 | Yes | Coaches | Demonstration site visits for Linked Learning Leads; milestone dates shown but excluded from capacity totals.
WBL Planning, Partnerships & Career Exposure | Annual WBL plan, priorities, checkpoints & year-end reflection |  |  | 1,3,7,9,11,12 | 2 | No | Coordinators | Combines annual planning, school checkpoints, next-year visioning, and reflection.
WBL Planning, Partnerships & Career Exposure | Employer/community partner outreach & industry partnership development | 2 | 12 |  | 2 | No | Coordinators | Ongoing employer outreach, onboarding, relationship development, and industry mapping.
WBL Planning, Partnerships & Career Exposure | Career Days, college/career fairs & pathway event planning/support | 3 | 11 |  | 3 | No | Coordinators | Major event-planning responsibility including industry partner recruitment and school support.
WBL Planning, Partnerships & Career Exposure | WBL connections for PBL and classroom learning | 3 | 11 |  | 2 | No | Coordinators | Industry speakers, partners, and career-connected experiences that support PBL units.
Internships & Work Readiness | School-site work readiness implementation support | 1 | 12 |  | 2 | No | Coordinators | Ongoing support for school implementation of work-readiness systems and student preparation.
Internships & Work Readiness | Work readiness PD, workshops & orientations |  |  | 3,4,5 | 2 | No | Coordinators | Staff/student-facing work readiness training, career-readiness workshops, and orientations.
Internships & Work Readiness | Student outreach, recruitment, applications, matching & placement | 3 | 9 |  | 3 | No | Coordinators | Consolidates student marketing/recruitment, applications, matching, interviews, and placement.
Internships & Work Readiness | Intern and worksite supervisor training/onboarding | 3 | 10 |  | 2 | No | Coordinators | Pre-placement and ongoing training for interns and worksite supervisors.
Internships & Work Readiness | Internship administration: timesheets, check-ins & ongoing support | 3 | 12 |  | 3 | No | Coordinators | Recurring timesheet processing and intern/worksite supervisor check-ins throughout placements.
Internships & Work Readiness | Teacher-led internship program support | 3 | 12 |  | 1 | No | Coordinators | Support for school-based/teacher-led internship programs beyond centrally managed placements.
Internships & Work Readiness | Internship closeout & program reflection | 11 | 12 |  | 2 | No | Coordinators | End-of-program closeout meetings and reflection with students/employers.
Internships & Work Readiness | Parent/student information & campus outreach | 2 | 5 |  | 1 | No | Coordinators | Information sessions, student/campus marketing, expectations, and communications.
Internships & Work Readiness | IRC / Workplace Readiness Badge implementation | 5 | 5 |  | 2 | No | Coordinators | Support for industry-recognized and workplace-readiness credentials tied to internship readiness.
WBL Operations, Logistics & Reporting | Field trip coordination, transportation & documentation logistics | 2 | 11 |  | 2 | No | Coordinators | Bus requests, approvals, documentation, follow-up, and trip logistics.
WBL Operations, Logistics & Reporting | Purchasing & procurement support | 1 | 12 |  | 2 | No | Coordinators | Quotes, purchase requests, purchase-order follow-up, and procurement troubleshooting.
WBL Operations, Logistics & Reporting | MiSiS/WBL data systems, reporting, compliance & training | 1 | 12 |  | 2 | No | Coordinators | MiSiS/WBL systems, rosters, reporting, compliance documentation, and scheduled trainings.
WBL Operations, Logistics & Reporting | Summer Bridge program support | 12 | 1 |  | 2 | No | Coordinators | Recurring summer program support; scope varies by year.
Note on C4: Microsoft Office User: 1=Jul, 2=Aug, 3=Sep, 4=Oct, 5=Nov, 6=Dec, 7=Jan, 8=Feb, 9=Mar, 10=Apr, 11=May, 12=Jun. Use Start/End for continuous activities.
Note on D4: Microsoft Office User: 1=Jul, 2=Aug, 3=Sep, 4=Oct, 5=Nov, 6=Dec, 7=Jan, 8=Feb, 9=Mar, 10=Apr, 11=May, 12=Jun. Use Start/End for continuous activities.
Note on E4: Microsoft Office User: For non-contiguous activities. Type comma-separated month numbers, e.g. "8,10,1,3" for Aug, Oct, Jan, Mar. If filled in, this OVERRIDES Start/End. Leave blank for continuous activities.
Note on F4: Microsoft Office User: 1=Light, 2=Moderate, 3=Heavy, 4=Peak. Used for Load row totals.
Note on G4: Microsoft Office User: Yes for one-day events / hard deadlines. Milestones don't count toward Load totals.

## Gantt
CTE – Linked Learning · Team Capacity Gantt
2026–27 school year · Auto-rendered from the Activities tab. Edit there to update this view.
Workstream | Activity | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
CTE Pathway, Scheduling & Funding | CTE master scheduling, pathway completion & Elevate error review | 🌱 CTE master scheduling, pathway completion & Elevate error review ● | 🌱 CTE master scheduling, pathway completion & Elevate error review ● | 🌱 CTE master scheduling, pathway completion & Elevate error review ● | 🌱 CTE master scheduling, pathway completion & Elevate error review ● | 🌱 CTE master scheduling, pathway completion & Elevate error review ● | 🌱 CTE master scheduling, pathway completion & Elevate error review ● | 🌱 CTE master scheduling, pathway completion & Elevate error review ● |  | 🌱 CTE master scheduling, pathway completion & Elevate error review ● |  |  | 🌱 CTE master scheduling, pathway completion & Elevate error review ●
CTE Pathway, Scheduling & Funding | Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support |  | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●● | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●● | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●● |  |  | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●● | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●● | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●● |  |  | 🌱 Unified Funding Application cycle: orientation, troubleshooting, application & purchasing support ●●
CTE Pathway, Scheduling & Funding | GSPP planning, implementation & spending support |  |  | 🌱 GSPP planning, implementation & spending support ●● |  | 🌱 GSPP planning, implementation & spending support ●● | 🌱 GSPP planning, implementation & spending support ●● | 🌱 GSPP planning, implementation & spending support ●● | 🌱 GSPP planning, implementation & spending support ●● | 🌱 GSPP planning, implementation & spending support ●● |  | 🌱 GSPP planning, implementation & spending support ●● | 🌱 GSPP planning, implementation & spending support ●●
CTE Pathway, Scheduling & Funding | Course equivalencies development |  | 🌱 Course equivalencies development ●● | 🌱 Course equivalencies development ●● | 🌱 Course equivalencies development ●● | 🌱 Course equivalencies development ●●
Instructional Design, PBL & Defenses | PBL/HQIM annual planning, pilot reflection & improvement design | [10 empty] | 🌱 PBL/HQIM annual planning, pilot reflection & improvement design ● | 🌱 PBL/HQIM annual planning, pilot reflection & improvement design ●
Instructional Design, PBL & Defenses | PBL/HQIM school-site coaching and professional learning |  |  | 🌱 PBL/HQIM school-site coaching and professional learning ●●● | 🌱 PBL/HQIM school-site coaching and professional learning ●●● | 🌱 PBL/HQIM school-site coaching and professional learning ●●● | 🌱 PBL/HQIM school-site coaching and professional learning ●●● | 🌱 PBL/HQIM school-site coaching and professional learning ●●● | 🌱 PBL/HQIM school-site coaching and professional learning ●●● | 🌱 PBL/HQIM school-site coaching and professional learning ●●●
Instructional Design, PBL & Defenses | Linked Learning onboarding / August PBL professional learning |  | 🌱 Linked Learning onboarding / August PBL professional learning ●●
Instructional Design, PBL & Defenses | PBL 101 / fall instructional training |  |  |  | 🌱 PBL 101 / fall instructional training ●●●
Instructional Design, PBL & Defenses | Defense calibration, support, feedback & reflection | [6 empty] | 🌱 Defense calibration, support, feedback & reflection ●● | 🌱 Defense calibration, support, feedback & reflection ●● | 🌱 Defense calibration, support, feedback & reflection ●● |  | 🌱 Defense calibration, support, feedback & reflection ●●
Pathway Strategy, Data & Certification | Administrator goal-setting, priorities & annual data review | 👥 Administrator goal-setting, priorities & annual data review ●● | 👥 Administrator goal-setting, priorities & annual data review ●● | [9 empty] | 👥 Administrator goal-setting, priorities & annual data review ●●
Pathway Strategy, Data & Certification | School goal progress checks and targeted support planning |  |  |  | 👥 School goal progress checks and targeted support planning ●● | 👥 School goal progress checks and targeted support planning ●● | [5 empty] | 👥 School goal progress checks and targeted support planning ●●
Pathway Strategy, Data & Certification | Linked Learning certification planning & school support |  | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●● | 👥 Linked Learning certification planning & school support ●●
Pathway Strategy, Data & Certification | Team data checks, accomplishments review & next-year goal setting |  |  | 👥 Team data checks, accomplishments review & next-year goal setting ● |  |  |  | 👥 Team data checks, accomplishments review & next-year goal setting ● |  |  |  | 👥 Team data checks, accomplishments review & next-year goal setting ● | 👥 Team data checks, accomplishments review & next-year goal setting ●
Pathway Strategy, Data & Certification | Cross-team funding review & GSPP 3-year planning | [8 empty] | 👥 Cross-team funding review & GSPP 3-year planning ● |  |  | 👥 Cross-team funding review & GSPP 3-year planning ●
Professional Learning & Leadership | Linked Learning Team retreat | 👥 Linked Learning Team retreat ●
Professional Learning & Leadership | Linked Learning Leaders professional learning series |  |  | 🌱 Linked Learning Leaders professional learning series ●● | 🌱 Linked Learning Leaders professional learning series ●● |  |  | 🌱 Linked Learning Leaders professional learning series ●● | 🌱 Linked Learning Leaders professional learning series ●● |  | 🌱 Linked Learning Leaders professional learning series ●●
Professional Learning & Leadership | Linked Learning microcredential program | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ● | 🌱 Linked Learning microcredential program ●
Professional Learning & Leadership | Administrator Linked Learning information sessions | 🌱 Administrator Linked Learning information sessions ●● | 🌱 Administrator Linked Learning information sessions ●● | 🌱 Administrator Linked Learning information sessions ●●
Professional Learning & Leadership | LL Conference, Showcase & recognition activities |  |  |  | 👥 LL Conference, Showcase & recognition activities ●● |  |  |  |  | 👥 LL Conference, Showcase & recognition activities ●● | 👥 LL Conference, Showcase & recognition activities ●●
Professional Learning & Leadership | Department planning, team committees & cross-functional coordination |  | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ● | 👥 Department planning, team committees & cross-functional coordination ●
Professional Learning & Leadership | School Redesign Grant demonstration site visits |  |  | 🌱 School Redesign Grant demonstration site visits ●● |  | 🌱 School Redesign Grant demonstration site visits ●● |  |  |  | 🌱 School Redesign Grant demonstration site visits ●●
WBL Planning, Partnerships & Career Exposure | Annual WBL plan, priorities, checkpoints & year-end reflection | ⚙️ Annual WBL plan, priorities, checkpoints & year-end reflection ●● |  | ⚙️ Annual WBL plan, priorities, checkpoints & year-end reflection ●● |  |  |  | ⚙️ Annual WBL plan, priorities, checkpoints & year-end reflection ●● |  | ⚙️ Annual WBL plan, priorities, checkpoints & year-end reflection ●● |  | ⚙️ Annual WBL plan, priorities, checkpoints & year-end reflection ●● | ⚙️ Annual WBL plan, priorities, checkpoints & year-end reflection ●●
WBL Planning, Partnerships & Career Exposure | Employer/community partner outreach & industry partnership development |  | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●● | ⚙️ Employer/community partner outreach & industry partnership development ●●
WBL Planning, Partnerships & Career Exposure | Career Days, college/career fairs & pathway event planning/support |  |  | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●● | ⚙️ Career Days, college/career fairs & pathway event planning/support ●●●
WBL Planning, Partnerships & Career Exposure | WBL connections for PBL and classroom learning |  |  | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●● | ⚙️ WBL connections for PBL and classroom learning ●●
Internships & Work Readiness | School-site work readiness implementation support | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●● | ⚙️ School-site work readiness implementation support ●●
Internships & Work Readiness | Work readiness PD, workshops & orientations |  |  | ⚙️ Work readiness PD, workshops & orientations ●● | ⚙️ Work readiness PD, workshops & orientations ●● | ⚙️ Work readiness PD, workshops & orientations ●●
Internships & Work Readiness | Student outreach, recruitment, applications, matching & placement |  |  | ⚙️ Student outreach, recruitment, applications, matching & placement ●●● | ⚙️ Student outreach, recruitment, applications, matching & placement ●●● | ⚙️ Student outreach, recruitment, applications, matching & placement ●●● | ⚙️ Student outreach, recruitment, applications, matching & placement ●●● | ⚙️ Student outreach, recruitment, applications, matching & placement ●●● | ⚙️ Student outreach, recruitment, applications, matching & placement ●●● | ⚙️ Student outreach, recruitment, applications, matching & placement ●●●
Internships & Work Readiness | Intern and worksite supervisor training/onboarding |  |  | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●● | ⚙️ Intern and worksite supervisor training/onboarding ●●
Internships & Work Readiness | Internship administration: timesheets, check-ins & ongoing support |  |  | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●● | ⚙️ Internship administration: timesheets, check-ins & ongoing support ●●●
Internships & Work Readiness | Teacher-led internship program support |  |  | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ● | ⚙️ Teacher-led internship program support ●
Internships & Work Readiness | Internship closeout & program reflection | [10 empty] | ⚙️ Internship closeout & program reflection ●● | ⚙️ Internship closeout & program reflection ●●
Internships & Work Readiness | Parent/student information & campus outreach |  | ⚙️ Parent/student information & campus outreach ● | ⚙️ Parent/student information & campus outreach ● | ⚙️ Parent/student information & campus outreach ● | ⚙️ Parent/student information & campus outreach ●
Internships & Work Readiness | IRC / Workplace Readiness Badge implementation |  |  |  |  | ⚙️ IRC / Workplace Readiness Badge implementation ●●
WBL Operations, Logistics & Reporting | Field trip coordination, transportation & documentation logistics |  | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●● | ⚙️ Field trip coordination, transportation & documentation logistics ●●
WBL Operations, Logistics & Reporting | Purchasing & procurement support | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●● | ⚙️ Purchasing & procurement support ●●
WBL Operations, Logistics & Reporting | MiSiS/WBL data systems, reporting, compliance & training | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●● | ⚙️ MiSiS/WBL data systems, reporting, compliance & training ●●
WBL Operations, Logistics & Reporting | Summer Bridge program support
Coaches | Effort load: Coaches + Both | 6 | 13 | 19 | 21 | 14 | 10 | 17 | 15 | 17 | 7 | 9 | 10
Coordinators | Effort load: Coordinators + Both | 10 | 16 | 33 | 34 | 34 | 27 | 30 | 27 | 32 | 25 | 26 | 20
Overall | Effort load: Coaches + Coordinators + Both | 14 | 24 | 48 | 48 | 43 | 34 | 43 | 39 | 43 | 28 | 32 | 26

## Legend & how to use
How to use this workbook
To add an activity:
Go to the Activities tab, scroll to the first empty row, and fill in Workstream, Activity, then EITHER Start month + End month (for continuous activities) OR Custom months (for irregular ones). Then add Effort and Milestone. The Gantt updates automatically.
Continuous vs. irregular activities:
If an activity runs continuously (e.g., Aug through Dec), use Start month and End month. If an activity happens at irregular intervals (e.g., Aug, Oct, Jan, and Mar), leave Start/End blank and type "8,10,1,3" in the Custom months column. Custom months overrides Start/End if both are filled.
To remove an activity:
Delete the row contents on the Activities tab. The Gantt bar disappears.
To shift dates:
Change the Start/End numbers, or edit the Custom months list. Bars update on the Gantt.
Months use 1–12:
1=Jul, 2=Aug, 3=Sep, 4=Oct, 5=Nov, 6=Dec, 7=Jan, 8=Feb, 9=Mar, 10=Apr, 11=May, 12=Jun.
Effort levels (1–4):
1=Light, 2=Moderate, 3=Heavy, 4=Peak. Active Gantt cells show effort as dots under the activity name. The bottom rows separately total effort for Coaches, Coordinators, and Overall by month. Milestones are shown on the Gantt but are excluded from Load totals.
Mark 'Yes' for single-day events or hard deadlines. They appear as dark cells on the Gantt and don't count toward Load totals.
Workstream colors:
The seven workstreams separate the major coach, coordinator, and shared bodies of work so overlaps are easier to interpret.
Workstream colors
CTE Pathway, Scheduling & Funding
Instructional Design, PBL & Defenses
Pathway Strategy, Data & Certification
Professional Learning & Leadership
WBL Planning, Partnerships & Career Exposure
Internships & Work Readiness
WBL Operations, Logistics & Reporting
Effort scale
1 | Light | Routine activity, minimal coordination
2 | Moderate | Standard workstream with regular touchpoints
3 | Heavy | Multiple deliverables, significant coordination
4 | Peak | Heavy lift; multiple deadlines or events converge
Team impacted
🌱 | Coaches
⚙️ | Coordinators
👥 | Both